## v1.0
Date | Item | comments | Status
2013-09-11 | ic_launcher.png | Need to change the pixels for mdpi, ldpi, hdpi | 30/11:Need to complete for launcher icon
30/11/13 | Hint text for person names | Hint text should auto wrap when it goes beyond the screen size | 30/11: Identify the method of achieving this
18/1/14 | Center the error message for no report |  | Done [19/1/14]
| Add action to expense table | Or add long click listener to table row
| Add Edit & delete report & expense functionality | In progress
update the logic for fetching person names from shared expense dialog
| Move Total expense incurred to the top of view expense |  | Done [19/1/14]
| Add validation error message to View Report fragment |  | Done [19/1/14]
| Add action to View Individual expense |  | Done [6/2/14]
| Add functionality for Reset button in Add report |  | Done [25/1/14]
| Shared expense table view correction |  | Done [29/1/14]
| Add Scroll view to View Individual Fragment dialog |  | Done [2/2/14]
| Add Header to View Report Fragment |  | Done . In a different manner [6/2/14]
| Remove the duplicate code from DBHelperModel class |  | Done [6/2/14]
| Add a validation to Add report fragment that no duplicate combination of report name , start date cannot be entered |  | Done [7/2/14]
| Implement delete report functionality |  | Done [8/2/14]
| Update the data model to validate the duplicates |  | Done [7/2/14]
| Check the database leak | No need. Causing no impact in real time

## v2.0
Date | Item | comments | Status
2014-03-03 | Order the report by recent start and end date [while viewing the report]
Add Vertical scrollbar for View Individual expense Dialog [Day wise expense]
Add check box to Add Person names fragment to get the person names from previous reports
Update manifest.xml with 2.0
Modify the UI in Shared Expense Dialog [Need to change from Drop down to check box]
Add alert dialog when switching between unfinished activities
Minimize the width of Next button in Add Report
Add settings if possible use it
Add styles and back ground color if possible [after reading / understanding]
Add option to archive the existing reports instead of deleting it.
Update the app name to Expense Manager if required
In Add expense , Refresh the dynamic table based on the expense amount
Implement Edit , delete functionalities for expense , Reports
In View Expense report, remove Type and sharing Count columns
Increase the width of free text (comments column , name field)
Don’t wrap the text in Comments field based on new line @ every 10th character

## Features
Date | Item | comments | Status
31/8/2014 | Sync app in multiple devices | Possible use of Parse Cloud API
Add export functionality into Word , PDF and other supported formats
| Define a format to insert expense and report, when given from outside the app | Read Messaging API , Notes .etc
| Link one expense report with other | Define certain rules and limitation here
Provision to add a master members list from which select list for a report
| Option to determine expense ratio based on the feeded contribution ratio | For eg : In real time , If one member willing to contribute 50 % of total expense , then divide the remaining expense into remaining people